## Slide 1
Steps in QI
Step 1: Identifying a problem, forming a team and writing an aim statement
Step 2: Analyzing the problem and measuring quality of care
Step 3: Developing and testing changes
Step 4: Sustaining improvement
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Highlight that this course is designed to teach a new skill – how to use quality improvement methods to improve service delivery at the point of care in your health facility
We will spend Day 1 working through the four steps of QI using a hypothetical example
On Day 2 we will help plan an initial QI project that you can carry out in your facility
The first step is to pick something specific to work on, form a team and develop a precise aim statement to guide your efforts.

## Slide 2
Step I : Learning objectives
You will learn
  How to review data to identify problems
  How to prioritize which problems to work on
  How to form a team to work on that problem
  How to write a clear aim statement
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Review the learning objectives for the first step, together we will learn How to review data to identify problems
How to prioritize which problems to work on
How to form a team to work on that problem
How to write a clear ‘aim statement’

## Slide 3
Identifying a problem to solve
Data-based: Review local health facility data and identify gaps related to quality of care
Simple and easy to change
Value for patient outcomes
Does not need many new resources
Not a rare event. Higher frequency. More patients affected.
Short turn-around time  early success is motivating
Avoid long-term projects initially
  Decreasing maternal mortality in a small facility:
  Decreasing hemorrhagic disease in newborn (vitamin K related): since onset is late, follow up after discharge is required to capture this
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Use the local data (from your workplace) to identify problems related to quality of care. You may be able to identify several problems.
Since QI is a new skill for many people it is important to think of the first improvement project as an opportunity for learning.
Because of this, new teams should work on QI problems which:
Are easy to solve by themselves
Do not need many additional resources to solve
Have a fast turn-around time (so you can get results quickly)
Is crucial for good outcome of patient care
You can leave more complex, long-term projects for later, when you have built stronger skills in using QI methods

## Slide 4
Select your team
Look for volunteers who are:
Enthusiastic - they want to make changes
Involved - they are the ones doing the work that needs change
Influential - others people listen to them and they can get things done
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Once you have picked a QI problem to solve, you need to pick a team of people who can work on this together. Look for people who are:
Enthusiastic – try to get members who want to work on this aim and have ideas for how to reach it . Look for Volunteers– people who are interested in making changes and are self – motivated
Involved – make sure most of the people on the team are doing the hands-on work that needs to change. People do not like being told to change but they like changing and improving themselves. Having more workers rather than managers will make it easier to change practice.
Influential – look for team members who are able to involve and influence other people

## Slide 5
Select your team
Identify who should be in the team:
Need people from every level: from administrators to cleaners
From all involved departments
Assign some key roles
  Leader
  Recorder
  Communicator
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: You should have a diverse range of people on the team – staff such as cleaners and janitors can also contribute depending on the identified problem.
Similarly, you may need to include community members (e.g. people accompanying the patients).
Titles and hierarchy should not matter
You want people who understand the problem and have the ability to change how care is delivered
It is also good to assign different roles:
Leader – lead meetings, direct activities to achieve goals, represent the team
Recorder - Record meeting notes
Communicator: communicates and liases among members

## Slide 6
Why is teamwork important for improvement ?
Healthcare is delivered by a range of people in the hospital
Given the opportunity, staff can identify problems and generate ideas to resolve them
Participation improves ideas, increases buy-in, and reduces resistance to change
Accomplishing things together increases the confidence of each member
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Healthcare is delivered by a range of people. Healthcare workers who will have to change how they work (their existing practices) should be in the team
Involving different cadres will lead to a wider range of ideas for how to fix problems, thus increasing chances of success
Involving people in the process of change early reduces resistance to change
People do not like to be changed by others but are willing to change when they get to decide how to change
Accomplishing things together leads to increased team spirit and confidence to address bigger problems subsequently
There is no ideal size of a team. Generally, a good team comprises 6-9 members. Keeping too many or too few may be less effective, even harmful for the project

## Slide 7
Aim statement Characteristics of a good aim statement
States a clear, specific aim –’what’ are we improving
Linked to specific patient population – ‘who’ will be affected
Should include a goal – ‘how much’ will we improve
  Neither too difficult nor too long to achieve
Includes a timeline – ‘by when’ will the goal be achieved
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Once your team is formed, jointly develop a precise aim statement that clearly states what needs to be achieved.
Review the characteristics of a good ‘aim statement’. It should:
Be linked to a particular patient group – e.g. newborns, women in labour
Include what needs to change/be achieved
Should be measureable and include a clear achievable target/goal: e.g. increase coverage from 20% to 80%
Include a definitive timeline

## Slide 8
SMART Aim
Specific
Measurable
Achievable (but challenging)
Relevant and recorded
Timely
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: When you develop an aim statement just think of the word SMART.
Any aim you develop should be as per the SMART criteria:
Review the SMART criteria from the slide

## Slide 9
Aim statement Problem: All babies are not dried immediately after birth
We will increase immediate drying at birth in 100% of live births from current 60% within 4 weeks, from 1st May to 1st June.
Who (which patients)- Newborn
What (the process)- Immediate drying
How much (the amount of desired improvement)- from 60% to 100%
By when (time over which the improvement will occur)- within 4 weeks (mention specific dates)
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Example 1: Go through the example of the aim statement and highlight how it has all the essential elements

## Slide 10
Aim statement Problem: Babies are cold at one hour following birth
We will reduce the percentage of newborns with low temperature (<36.5 C ) from current 50% to <10% within 6 weeks, from 15th June to 30th July.
Who (which patients) - Newborns
What (the outcome) - Hypothermia (<36.5 C)
How much (the amount of desired improvement) - from baseline of 50% to <10%
By when (time over which improvement will occur)- within 6 weeks (with dates)
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Example 2: Go through the example of the aim statement and highlight how it has all the essential elements

## Slide 11
To establish skin to skin contact after delivery in low risk mothers admitted in Labour Room
To establish skin to skin contact immediately after delivery for at least one hour from 0% to 50% within four weeks (Jan 1st to Feb 1st) for newborns of low risk mothers admitted in Labour Room
Is this a good aim statement
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Discuss how the first aim statement
is not specific (does not define what is meant by skin-to-skin contact)
is not measurable (does not have a target) and
does not have a timeline.
The second aim statement is good. It provides:
a clearer definition of what is meant by skin-to-skin contact
a target – “from 0% to 50%”
a timeline – “within 4 weeks”

## Slide 12
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work

## Slide 13
Steps in QI
Step 1: Identifying a problem, forming a team and writing an aim statement
Step 2: Analyzing the problem and measuring quality of care
Step 3: Developing and testing changes
Step 4: Sustaining improvement
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Now that you have selected a problem to work on, formed a team and developed a clear aim statement it is time to move to the second step:
Analysing the problem and measuring quality of care

## Slide 14
Step 2 Learning objectives
You will learn
Tools for understanding processes and systems of healthcare
How using these tools can help identify the causes of and possible solutions to reach your aim
How to develop indicators for process and outcome of care
How to use indicators to track progress of improvement
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: In Step 2 you will learn how to identify the causes for the selected problem and to develop indicators to measure progress in reaching your aim.
Read the four learning objectives from the slide.

## Slide 15
Step 2: Importance of Analysis
Explore in detail possible causes of a problem
Helps focus on things that are within our control
Gives an opportunity for everyone to give their insights based on their role in the process
Helps us understand what is happening in the system at present and thus identify possible solutions
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Review some key reasons why analysis is important in quality improvement.
When you see a patient, you are not interested in just treating the symptoms; you also want to identify the real cause of the symptoms so that you can treat appropriately. The same applies when you are working on a problem in the health facility.
.

## Slide 16
Tools for analysis
Understanding the current system:
        Fishbone
        Five Why’s
        Pareto Principle
        Process Flowchart
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: We will cover four tools for problem analysis in this Step.
We are going to discuss options for identifying possible causes of the problem that you have decided work on. By broadening the understanding of all underlying main causes you will come up with appropriate solutions that are likely to succeed.

## Slide 17
1. Fishbone : Identify all possible contributing factors
Why might a problem be happening?
        People
        Places
        Procedures (practices)
        Policies
        anything else
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: One way to determine the possible causes of the problem is to draw the Fishbone Diagram. (a completed diagram looks like the skeleton of a fish!).
In general, there are four broad categories of causes for any observed problem.
PEOPLE – people may not know what to do or how to do it
PLACE – the place you are doing the work may make it hard to do the work. For example, there may be no equipment or equipment is kept too far from where it is needed
PROCEDURE – the way work is done may be contributing to the problem. For example, tasks are being done in the wrong order or at the wrong time
POLICY – there may be no policies, or policies may be wrong or non-specific

## Slide 18
1. Fishbone : Identify all possible contributing factors
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Steps to draw a fishbone with your team:
Write the problem in a box on the right-hand side of a large sheet of paper, and draw a line across the paper horizontally from the box so that it looks like the head and spine of a fish.
Next, draw a line off the “spine” of the fish and write down contributing factors. These may be different levels of the health systems, or building blocks of the system, such as people (staffing), place (equipment), procedure, policies (guidelines) etc.
Now, for each of the contributing factors, identify possible causes. Show these possible causes as shorter lines coming off the "bones" of the diagram.
Where a cause is large or complex, then it may be best to break it down into sub-causes. Show these as lines coming off each cause line.
By this stage, the fishbone should show several possible causes of the problem.

## Slide 19
2. “Five whys”
Understanding why something is the way it is:
Mothers are not breastfeeding – Why?
They feel uncomfortable taking their gown off – Why?
The gown opens at back, so they have to take entire gown off to breastfeed, so they feel uncomfortable.
  Why they have this type of a gown?
That is what store keeper orders.
  Why doesn’t the store keeper order gowns appropriate for breast feeding?
Because no one has requested him to do that
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Another tool is the ‘Five Why’s” - this is used to identify the root-cause. Doing five whys involves asking ‘why’ a problem exists and then continuing to ask ‘why’ after each answer until you identify a possible way of fixing the problem
For example: A hospital is trying to increase the number of women who start early breastfeeding within the first hour of birth. Using the five whys analysis the team was able to understand that the type of gowns that they are giving the women in labour make it difficult for the women to breastfeed.
Continuing to ask ‘why’ helps the team identify why they have that type of gown (because no one had ever asked for a different type of gown) and to come up with a solution (ask the store keeper to order another type of gown for breastfeeding mothers)

## Slide 20
2. “Five whys”
Understanding why something is the way it is
Alternative Scenario
Mothers are not breastfeeding – Why?
They feel uncomfortable taking their gown off Why ?
There is no privacy to breast feed, so they feel exposed. Why is there no privacy to breastfeed?
They are in a common ward. There are no curtains or separate covered space for privacy for breastfeeding
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: There is no one perfect answer to a Five Why’s analysis. It is not necessary to ask Why 5 times. It can be less or more.
Additionally you might get a different chain of answers depending on the perspective of various people on the team.
The key is to understand better why things are they way they are and reach to an actionable cause for the problem.

## Slide 21
3. Pareto Principle
80% of the problem is due to 20% of the causes
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Video on Pareto chart
Notes: The Pareto Principle states that 80% of a problem is due to 20% of the causes. This principle helps you to look for the causes that account for most of the problem and to prioritize the ones that you can address efficiently.
Show video on pareto chart

## Slide 22
v
Pareto Chart Example: Medication Error
Chart: 
| Prescription Error | Improper Storage | Dilution Error | Wrong Label | Missed Dose | Wrong Dose | Expired Drug | Wrong Patient | Wrong Route
% | 45 | 20 | 15 | 6 | 5 | 3 | 3 | 2 | 1
#REF! | 1
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
80% of the problem is due to 30% of causes
Notes: In this problem of medication errors, there are nine reasons for the error but only three causes account for 80% of the errors. Working on these three causes will be more efficient than working on the other, less frequent causes.

## Slide 23
4. Process flowchart
How to develop a process flow chart
Decide the beginning and end points of the process being improves
Identify the steps of the process as done at present
Link the steps with arrows showing direction
Now review the flowchart to see whether the steps can be improved upon to achieve the end point efficiently:
  are some steps unnecessary?
  can the order of steps be changed to make things better / easier?
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: The process flow chart describes all the steps in a process. For example, how essential newborn care is provided immediately after the delivery.
Flow charts can help identify problems in the process, e.g.
Steps that are being done in the wrong order
Unnecessary or repetitive steps
Steps that are contributing the most to the problem
Creating a flow chart involves
Deciding on the beginning and end of the process you are trying to explain. For example, delivery of a baby (start) to baby leaving the labour room (end).
All the steps between those points. For example, baby being dried, skin-to- skin care, starting breast- feeding etc.
Linking the steps together with arrows
Reviewing the whole sequence to check if this is really what happens

## Slide 24
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Steps
Option
(diamond)
Yes
No
Step not clear
(cloud)
Start
(oval)
Steps of the process (rectangles)
Steps
Steps
Start
(oval)
Steps
Notes: Different shapes are used to visualize the steps of a process (process mapping) in a flow chart:
start and finish (oval)
routine actions that always happen (rectangles)
option points (diamonds) – these are steps that lead to different options:
  Either someone makes a decision about what happens next (e.g. a triage step)
  Or the care in that step does not always happen (e.g. only 50% of women get oxytocin in the first minute after delivery)
unclear steps (clouds) these are used when you are not sure what happens

## Slide 25
Key tips for analysis
Analysis helps identify several causes of the problem
Try to find few causes that account for most of the problem
Focus on causes that are within our control and possible to remedy
Use these tools to stimulate discussion among team members
Involve all team members in the analysis
Think about how re-organization can help improve the process
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Emphasize that we have learnt four tools – Fish Bone, “Five Whys”, Pareto Principle, and Process flow chart.
These tools can help identify appropriate solutions to address the main causes of the problem that you are trying to solve.

## Slide 26
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work

## Slide 27
Step 2: Analyzing and measuring quality of care
How to develop indicators for process and outcome of care
How to use indicators to progress of track improvement
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: We have used the diagnostic tools to learn what the most important causes of the problem are.
We now need to develop indicators so we can learn if we are making progress in solving our problem

## Slide 28
Why measure?
To know whether or not we have an improvement
Helps us know how we are progressing in achieving our aim
Data is objective – helps communicate with others and among the team
Helps us to compare how we are doing over time
Data allows us to make comparisons with other units / facilities
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Discuss the importance of measurement in quality improvement.
Indicators help us to understand how we are currently doing in providing care and help us to plan what to do next
They also allow us to compare our performance with other health facilities that are working on similar problems.
This can help to identify lessons that we can take from other facilities.

## Slide 29
Process and outcome indicators
An indicator defines a rate/ratio or an event
Measure of Process – “actions that are taken in delivery of care”
  Washing hands
Measure of Outcome - “the result of the actions taken…”
  Incidence of infection in the patients
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Review what is a Process and what is an Outcome. For example, a QI team may try to reduce the incidence of infection (an outcome) by improving hand washing (a process)
Process indicators measure actions that health workers or others carry out to achieve something. Process measures let you know if you are putting into practice the process or not.
For example, the % of health workers washing their hands tells you how effective the team is at improving hand-washing behavior
Outcome indicators measure what health workers are trying to achieve (clinical outcome). Outcome measures let you know if you are actually getting the result that you want.
For example, the % of newborns with infection tells you if hand washing is working or not.

## Slide 30
Process and outcome indicators?
You measure process
  To learn whether the action you want done is really happening or not
You measure outcome
To learn whether the action is really leading to the desired patient outcome or not
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Ideally QI projects should measure both process and outcome because they give different information:
Emphasize that while you want answers to both of these questions on the slide you should look for the easiest way of getting data. It may not always be required or feasible to have both process and outcome indicators for a QI project.
It is possible that there are more than one processes that need to be addressed. If the hand washing indicator shows good performance and there is still a high rate of infection, the team would need to look for other causes of infection.

## Slide 31
Qualities of a good indicator
Clear and unambiguous (teams will not confuse what is meant by a particular indicator)
Should be linked to aims
Should be used to test change and guide improvement
Should be integrated into team’s daily routine
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Indicator has to be clear and precise so that everyone can understand it in the same way and knows how to measure it.
This includes having a well-defined numerator and denominator.
It is also important to decide as a team who should collect the data, where from and how data will be collected and how often you should collect and review the data

## Slide 32
Developing indicators
% women with post- partum hemorrhage
Patients in hospital
Patient gets treated
Result
DENOMINATOR
Number of women delivering in hospital
PROCESS
Percentage of women receiving Inj. Oxytocin within 1 min of delivery
OUTCOME
Percentage of women with post-partum haemorrhage
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: To start developing an indicator the first step is to understand what is happening in the system.

## Slide 33
Example of good indicator
Indicator: The rate of PPH in women in the hospital
  Numerator: Number of cases of PPH
  Denominator: Number of women giving birth
  Source: Labour room register in the health facility
  Person responsible: Delivery room nurse
  Frequency: Labour room register will be reviewed monthly
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Here is an example of a good indicator. It specifies the numerator, denominator, source, who is responsible for data collection and frequency of data for review.
It would be good to highlight here that monthly data review is okay for outcome indicators but you should look at process indicators daily or weekly to speed up the learning process.

## Slide 34
Developing indicators
Babies born
Babies receive care
Result
DENOMINATOR
Number of live babies born in facility
PROCESS
Percentage of babies dried immediately
OUTCOME
Percentage of babies hypothermic at 60 minutes after birth
% of babies getting skin to skin care at birth
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work

## Slide 35: Example of good indicator
Indicator: Percentage of babies being dried immediately after birth
  Numerator: # of babies dried immediately after birth
  Denominator: # of normal vaginal live births
  Source: Labour Room Register
  Person responsible: Delivery room nurse
  Frequency: Review at the end of every shift
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work

## Slide 36
Time-series chart:
Percentage of women receiving uterotonic within one minute
Chart: % of women receiving oxytocin in 1 minute
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Percent | 0.12 | 0.07 | 0.13 | 0.14 | 0.19 | 0.38 | 0.68 | 0.88 | 0.92 | 0.89 | 0.97 | 0.94 | 0.93 | 0.98 | 0.97 | 0.97
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Explain from the example of run chart in this slide. Something happened at week 5. Process of care was changed

## Slide 37
Plotting a time series chart
Title: Clear and well defined title including what and when
X and Y axis have clear scale and are labelled
  X axis: time - days/weeks/months
  Y axis: measurement in %, proportion or number
Annotation
Numerator and denominator values are shown
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: A good way to review data is to plot the it on a time series chart (or a run chart). Time-series charts allow you to see how the data are changing over time.
A time-series chart has the following components:
A clear title
Well-labelled x and y axes
The x or horizontal axis represents time. This is the time period that you are using to review your data
The y or vertical axis represents the percentage performance of the indicator. It is usually from 0 to 100%
It is also important to annotate on the chart the time points when you introduced specific change ideas so that cause – effect relation is clear.

## Slide 38
Key tips
Looking at data overtime is crucial
Frequent measurement (daily or weekly) is better than less frequent (monthly)
Only collect data what you are going to use
Don’t overburden with endless data collection
If possible, try to use data that are already recorded in your health facility or that will be easy to collect
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Summarize the use of indicators:
As far as possible, try to use data that are already collected in your health facility. This saves time and you can spend more time testing changes to improve care rather than collecting data
Only collect what you are using. We are collecting data to use it to learn. If you are not using it or not learning from it – do not collect it. Save the effort!
Also, we will learn faster if we review the data frequently. Every day or every week is much better than every month. As mentioned earlier, outcome indicators can be monitored once a month.

## Slide 39
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work

## Slide 40
Steps in QI
Step 1: Identifying a problem, forming a team and writing an aim statement
Step 2: Analysing the problem and measuring quality of care
Step 3: Developing and testing changes
Step 4: Sustaining improvement
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: We are at Step 3 now. By this time health facility teams have decided what they want to improve, formed a team, identified some of the causes for poor care and developed some measures to indicate how our project is progressing.
After diagnosing the problem the team now must take action/s to correct it.
This involves developing ideas about what to change to fix the problem.
We will also discuss how to test these ideas in our own work place to learn if they work and to adapt them to your setting

## Slide 41
Step 3 Learning objectives
You will learn
How to come up with ideas about what to change to reach your aim
How to plan a plan-do-study-act (PDSA) cycle to test change ideas
What to do as you learn from a PDSA cycle
How to test multiple change ideas to achieve your aim
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: State the learning objectives

## Slide 42
Develop changes
Determine possible change ideas that may lead to improvement
Ask your team.
  Based on the analysis what changes can we make?
  Why will this change result in an improvement?
  How will it work?
  What will we expect to see as a result of this change?
Organize changes according to importance and practicality
Test one change at one time
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: To find a solution for the identified problem the health facility team needs to:
Identify some changes (ideas) that they think will work in their situation
Review the possible change ideas if these are important for patient care and are likely to be effective and feasible at their workplace
Test the idea/s to learn if these work and to adapt them for your setting, as required
There may be many solutions that can be explored, but teams may choose to focus on solutions that are actionable within their sphere of influence in the short term, while advocating for more long-term systemic change

## Slide 43: Some categories of changes
Category | Description
Improve knowledge or skills | Training or standards
Eliminate waste | Stop doing useless or harmful things
Reassign tasks | Change who does what
Reorganize tasks | Do tasks in different order or different location
Improve patient relationship | Listen to what patients want
Reduce variation | Do things to make work more standard
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: There are several types of changes that you can make in your health facility. Some of the main categories include:
Eliminate waste by stopping unnecessary treatments or steps of care – stop doing harmful or useless (even if harmless) practices
Reorganizing the sequence of tasks or reassigning tasks to different staff.
Improve the patient relationship and communication - her experience of the care received – listen to what patients want
Manage variation in the existing treatment and care practices – make work (process of care) more standard and predictable

## Slide 44: Some categories of changes
Category | Examples
Improve knowledge or skills | Teach about the importance of skin-to-skin care to keep babies warm
Eliminate waste | Have equipment closer to hand to reduce time getting it
Reassign tasks | Share work between staff members
Reorganize tasks | Start skin to skin and dry babies before cutting the cord
Improve patient relationship | Learn from mothers how they would like care to be provided during delivery
Reduce variation | Triage new admissions in the labour room
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Examples of each category of changes are given.

## Slide 45
Testing Changes
What is a PDSA cycle?
- Is the change feasible?
- Did the change lead to improvement ?
PLAN
Plan the change
DO Test the change
STUDY What did you learn?
ACT Next steps on the basis of the test
Adopt,
Adapt,
Abandon
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Testing the change idea: It is rare that any change will work perfectly the first time. It will usually need some adjustment to work in your setting. Because of this, it is important to test the new ideas to learn how they work and to adjust them .
The PDSA cycle is very useful for this. PDSA stands for: Plan, Do, Study, Act. These are steps to take when testing a new idea
Plan –you decide how the change idea will be implemented.
Do – carry out the change
Study – the team reviews whether the desired change has been carried out as planned ; what they learned from the test; whether it was a success or a failure based on the collected data
Act – the team decides what to do next depending on the experience and result of implementing the change idea.

## Slide 46
Plan the test What will your team do ?
  Discuss and document the details for:
    What change idea will you test
    Who will make the change
    Where will this test be done
    When will the test be started
    For how long will this test be done
    How will we know whether this test happened as planned
    What do we expect to learn from this test?
P
D
S
A
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Planning a test
It is important to emphasize that a team can do small scale PDSA cycles very quickly.
For example, when someone is cooking and they decide to add salt and see if it tastes better they are doing a PDSA. Teams can do short PDSA cycles as well to learn how new ideas are working and to adapt them.

## Slide 47
Planning Example
What change will you test? | New protocol for post-partum assessment to pick up PPH earlier
Who will make the change? | Two of the nurses involved in developing the protocol
Where will they do it? | They will test the protocol in the post-partum ward
When will they test? | They will test it on their next shift
How long will they test? | They will test on one shift only
What do you want to learn? | Is it feasible to follow the protocol? Do we need to adapt the protocol? Do we need to change anything in the ward to make it easier to follow the protocol?
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Plan step of the PDSA cycle:
Share the example from the slide

## Slide 48: Do the test
Sometimes the plan might not happen exactly as envisioned.
Make sure you document exactly what happens as there is valuable learning happening while carrying out a test
P
D
S
A
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: “Do”
In this step the assigned persons in the team tests the change as per the plan developed in the previous step.
Often things do not happen as planned. It is important in the ‘Do’ step to document any challenges or deviations from the original plan.

## Slide 49
Study the learning from the test
After testing the change you need to think about:
  Was the test carried out as planned?
    If not why?
    What else needs to be done so this change can happen
  Is this change feasible in our setting
  Do we think it will solve the problem
  Does the change improve our indicator
P
D
S
A
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Study
The team reviews what they learned from the test: whether it is feasible in our work setting whether it was successful in addressing the problem as hypothesized by the team

## Slide 50
Act – Take action based on how the test went
After reviewing the results of the test the team decides whether the change should be:
  Adopted – The change worked well and led to improvements in the data and is feasible and acceptable.
  Adapted – The change idea worked partially but needs some modifications and further testing. This is usually the most common scenario.
  Abandoned – The change idea did not work at all.
P
D
S
A
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Act:
After studying the results of implementation the team will decide to:
Adapt the change – if it has not fully succeeded, make some modifications and implement again
Adopt the change – if it works perfectly make sure everyone in the health facility uses this change
Abandon the change – if it does not work at all or makes things worse so stop doing it

## Slide 51
Testing Changes
Test BIG changes on small scale
Test individual changes separately when possible
Negative results are opportunity to learn
Think about how conditions change over time (monthly, seasonal patterns, external variables)
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Testing on a small scale means that there won’t be any harm and provides an opportunity to learn. It also allows you to make modifications to your idea before you apply it at a large scale.
As much as possible, it is good to test each change idea individually otherwise you wont know which idea led to improvement and which one did not.
It is also important to highlight that some of your change ideas will not work. That is expected.
It is good to test the change/ idea in different working conditions to learn if the change always works, for example, testing on weekends or night time will let you know if changes will work when there are fewer staff.

## Slide 52
11111
Multiple changes towards a single aim
Aim: Reduce severe hypothermia in newborn babies by 50% in 3 months
Adapted from the Institute of Healthcare Improvement (IHI)
Staff educated and involved
Maintain ambient temperature
Transport incubator warmed before transfer
On job mentoring
Make ziploc bags available (abandon)
Switch off air conditioner in labour room prior to anticipated preterm birth
Orientation for new staff
Put wall thermometer in newborn corner
Revert to cling wraps and improve application
Maintain baby’s temperature
P D
S A
P D
S A
P D
S A
P D
S A
P D
S A
P D
S A
P D
S A
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: No QI project will reach its aim with only one PDSA. You will need to do multiple PDSA’s depending on your analysis and identified causes and change ideas.
In this example multiple change ideas were tested to reduce hypothermia in newborn babies. Some of these change ideas were abandoned (Ziploc bags), some were adapted or adopted.
Try to test one change at a time. The changes in the illustration can happen at different times in the health facility

## Slide 53
What to do after identifying successful change ideas?
While testing changes
Few people are involved
  less resistance
Rapid cycles
  take less time
Support needed low: Testers do not yet intend changes to be permanent
Tolerance for failure is high: A failed test is an opportunity to learn
Low certainty that the idea will work
While implementing changes
More people involved
  expect more resistance
Longer cycles
  More time, people, resources needed.
More support needed from all levels
Tolerance for failure is less
Implement only those changes that have been tested and show improvement in indicators
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Once you have identified a successful change idea by doing PDSAs you can then ‘implement’ the change across the unit or ward or health facility.
In quality improvement the term ‘implement’ refers to applying a successful change idea to a larger scale. You should only implement changes that have been shown to be successful in PDSA’s.

## Slide 54
Key tips
Change ideas will improve care, if
  1. They are based on analysis
  2. They are actually implemented and tested!
  3. Adapted to the local context by testing
Testing is important to make sure that:
  You selected the right change idea
  That the effect of the change is studied on a small scale
  Change ideas that are successful can be made routine practice and those that fail are abandoned
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Changes will lead to improved care if
They are the right changes (you may have made the wrong diagnosis of the problem when you analyzed it and therefore picked the wrong change idea)
They are put into action - if the team members including front line workers do not want to make the change or do not know how to test it then the change will not work. It is crucial to involve front- line workers in all steps.
They are adapted to the local context. Ideas from other settings may be good in theory but need to be tested to make sure that they work properly in the local setting and will many times need to be adapted
PDSA cycles (testing) are invaluable for making sure that:
You selected the right change
That the change is put into action after right planning
That the effect of the change is studied.
Changes that are successful are scaled up and those that fail are abandoned

## Slide 55
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work

## Slide 56
Steps in QI
Step 1: Identifying a problem, forming a team and writing an aim statement
Step 2: Analysing the problem and measuring quality of care
Step 3: Developing and testing changes
Step 4: Sustaining improvement
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: After fixing the problem the final step is to make sure that the improvement is sustained over time.

## Slide 57
Step 4 Learning objectives
You will learn how to
Build enthusiasm, motivate team, recognition by certificates and celebration
Share the results and successful projects widely
Make policy with new ways to work
Hardwire the gains by making system change
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Review the learning objectives

## Slide 58
Take specific actions to sustain improvement
Documenting the flow of the new process — the new way of doing things
Teaching people new ways to work
Making changes in job descriptions, policies, procedures
Assigning day-to-day ownership for the maintenance of the new process
Having senior leaders remove any barriers that might allow slipping back to the old process
Addressing supply and equipment issues related to the aim
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: Once you have found successful solutions that work it is important to take some concrete steps to make sure that they are sustained in the health facility.
Use the points from the slide to explain the elements that ensure the change becomes the standard way of working.

## Slide 59
Tinkering vs. System Change
Problem | Tinkering | System change
Physicians orders are illegible, causing medication errors | Encourage Physicians to write more clearly | Pre-printed standardized order sets to minimize need for hand writing
Oximeter alarms not set as ordered | Penalize nurses who are non compliant | Modify alarm defaults
Breast milk use is low for premature babies | Suggest hospital to hire lactation consultants | Analyze current process and make changes to improve use of breast pumps
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: To ensure that a change is sustained one has to ensure that it is a system change and not just a minor tinkering of the process.
Tinkering is reacting to the problem rather than looking for the root-cause and addressing that
Tinkering usually relates to trying to get health care workers to change only their immediate behavior rather than changing the system so that it becomes a norm for them to provide good quality care. Examples are given in the slide.

## Slide 60: Improvement is more likely to be sustained when:
The new way of working | Is easier Is obviously better Can be adapted as needed Is easy to measure and monitor
Front line workers | Were involved and allowed to develop the new way of working Have skills to monitor and adapt the new way of working
Unit and facility leadership | Are involved in the developing and sustaining the new way of working
Organization | Has structures and systems to support quality improvement Has structures and systems to support the new way of working
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: It is important to think of sustainability from the beginning. If the changes that you have tested require hard work and make things more burdensome for the staff or patients then they will not be sustained over a long time. Changes that make things easier and better for the staff and for the patients are likely to be sustained. Doing improvement work together as a team of frontline staff ensures ownership and ensures that the right change ideas are developed. Leadership support is important to sustain the gains and their support may be needed to make the new way of working the norm across the unit/facility. Although skills to improve care at the frontline are the cornerstone for quality improvement, we need to over time develop structures and systems at an organizational level to support quality improvement work and make things easier for the QI teams at the frontline.

## Slide 61: Building Enthusiasm for Improvement
Be smart about choosing your first project
Carry out the project!
Build your team. Do not work alone.
Keep higher ups informed.
Seek guidance from QI mentors / continue self-learning
Document your work so you can share it
Display your progress in the department on notice boards.
Involve new members and teach others the basics of improvement
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: It is critical to maintain momentum for quality improvement.
The most important way is to experience a successful quality improvement project. To achieve success in you project you have to be SMART about selecting your aim.
Also, there can be no improvement if you don’t carry out what you plan! So do the work and carry out your project.
Don’t try to do everything alone, the success of quality improvement depends on teamwork.
Keep seniors informed about your work and seek guidance from any available QI experts. There is lots of information online on quality improvement to build your own knowledge
Document your work in word or powerpoint in a timely manner so that you are later able to share it with others.
Display your successes prominently in your unit / ward to motivate your staff and team members.
Form multiple teams in the health facility so that they can learn and support each other

## Slide 62
Key to success
Local champion: A leader who respects others, is a keen listener, uses collective wisdom of the team rather than being directive, identifies & harnesses key strengths of members, sets example
Incentives: System rewards successful teams – e.g. certificates, ‘QI star of month’. Provides opportunities to disseminate and share successes
Personal aspirations: Most of us entered medical profession to reduce suffering and help society
Positive attitude: Being positive and prepared to address barriers, challenges which may prevent us in achieving the aim.
v
Step 1
Group Work
Step 2M
Step 2N
Group Work
Step 3
Step 4
Group Work
Notes: A champion is someone who takes ownership and leads the QI initiative in the health facility or in the health system.
Manager of the health facility should continuously encourage the health care team to improve quality of care by rewarding people who are involved in QI efforts and giving them opportunities to share their work.
Focus on the big picture. The point is not to mechanically pick aims, do fishbone exercise, draw charts and undertake PDSA cycles but to ensure best health outcomes for the patients.